## Instructions
Introduction
This spreadsheet has been created to assist Fire and Rescue Services when planning the implementation of this Fire Standard. It provides a facility to record actions that have been taken, or need to be taken, to move toward achieving the Fire Standard. When first completed, it will provide a benchmark from which progress over time can be measured.
The spreadsheet is inteded to used to assist FRS with their planning and implementation, but it will also provide useful evidence for HMICFRS inspections. Time-stamped versions of this spreadsheet will show progress being made with individual action points over time. The Dashboard provides a pictorial overview of the level of compliance.
The spreadsheet is a tool that is intended to assist services and they are therefore free to make any changes they wish in order to aid their planning and implementation of this Standard.
Instructions for Use
The spreadsheet has been set-up to record actions for each Criteria listed in the 'To Achieve...' section of the Fire Standard.
Criteria Tabs
1. Move to the Tab for Criteria 1. In column A, define the work that needs to be done to achieve complaince with the criteria (tasks). The template provides for up to 10 actions/tasks to be added, but further rows can be added to the table as required (down to row 50, after which some formulas on the Dashboard will stop working). Overtype 'Task 1/1' with an actual action/task. Even work that has already been completed can be recorded here to show the extend of the work that was carried-out.
2. In Column B, set the Priority for the action. Select high, medium or low from the drop-down list. Some tasks will be considered to be a higher priority than others, and this information will allow FRS to plan work to address high priority matters first. Lower priority matters can be addressed later.
3. In Column C, record the Impact that the Action will have on complaince. Select high, medium or low from the drop-down list. To progress an action plan in a timely manner, FRS may choose to address tasks likely to have the greatest impact first, alghough this information must also be considered in conjunction with the Priority (Column B).
4. In Column D, the level of compliance for each task should be recorded in the drop-down list. If the task requires new work and no progress has yet been made, then the task should be recorded as Non-compliant. If some work has been completed but the task is incomplete, then the the task should be recorded as Partially Compliant. And if all work is complete, the task should be recorded as Fully Compliant.
5. The cell in D2 will automatically update to reflect the lowest level of complaince that exists in the task below. This information is then used to populate the 'Overall Complaince' graph at the top of the Dashboard.
6. Repeat the process for each Criteria tab.
Dashboard
1. The Dashboard sheet has been locked (protected) to prevent accidental changes being made to formula. However, competent users can unprotect the sheet and make changes as required.
2. Only cells C4 to C7 allow data to be entered on the Dashboard, without unprotecting the sheet.
3. The Dashboard provides a summary view of the state of compliance against the standard. If versions are recorded over time, they will illustrate the progress being made. Easrly versions are likely to show high levels of non-compliance, with much work to be done. But later versions should show more tasks complete, with fewer outstanding. The doughnut graphs should change from Red, to Amber to Green over time.
4. The most significant graph on the Dashboard is the 'Overall Compliance' graph at the top. It provides an 'at a glance' overview of the state of complaince with the standard. It provides a summary of data in cell D2 on each criteria tab. For senior managers, this single graph provides the simplest indication of the state of play.
Hidden Lists Tab
There is one hidden tab on the spreadsheet which can be revealed if necessary by 'Unhiding' (right click on the tabs). It contains the data used in drop-down lists and is also used to collate some data used for graphs. The information on this sheet should not normally need to be altered, which is why the tab is normally hidden from view.
Introduction
This spreadsheet has been created to assist Fire and Rescue Services when planning the implementation of this Fire Standard. It provides a facility to record actions that have been taken, or need to be taken, to move toward achieving the Fire Standard. When first completed, it will provide a benchmark from which progress over time can be measured.
The spreadsheet is intended to be used to assist services with their planning and implementation, but it will also provide useful evidence for HMICFRS inspections. It is a tool that is intended to assist services and they are therefore free to make any changes they wish to aid their planning and implementation of this Standard.
Services can create time-stamped versions of this spreadsheet which will help them to show progress being made with individual action points over time.
The Dashboard provides a pictorial overview of the level of compliance and may support services with strategic level reporting.
Instructions for Use
The spreadsheet has been set-up to record actions for each Criteria listed in the 'To Achieve this Fire Standard' section of the Fire Standard.
Dashboard
1. The Dashboard sheet has been locked (protected) to prevent accidental changes being made to formula. Only cells C4 to C7 allow data to be entered on the Dashboard, without unprotecting the sheet. Competent users can unprotect the sheet and make changes as required. The password to unlock the sheet is: FireStandards.
2. The Dashboard provides a summary view of the state of compliance against the standard. If versions are recorded over time, they will illustrate the progress being made. Early versions are likely to show high levels of non-compliance, with much work to be done. But later versions should show more tasks complete, with fewer outstanding. The doughnut graphs should change from Red, to Amber to Green over time.
3. The most significant graph on the Dashboard is the 'Overall Compliance' graph at the top. It provides an 'at a glance' overview of the state of compliance with the standard. It provides a summary of data in cell D2 on each criteria tab. For senior managers, this single graph provides the simplest indication of the state of play.
Criteria Tabs
1. Move to the Tab for Criteria 1.
2. In column A, you will need to define each task/action that needs to be completed to achieve compliance with the criteria. The template provides for up to 10 actions/tasks to be added, but further rows can be added to the table as required (down to row 50, after which some formulas on the Dashboard will stop working).
3. In Column A, overtype 'Task 1/1' with your defined task/action. Even work that has already been completed can be recorded here to show the extent of the work that was carried out.
4. In Column B, set the Priority for the action. Select high, medium or low from the drop-down list. You may decide that some tasks will be a higher priority than others, and this information will allow you to plan work to address high priority matters first. Lower priority matters can be addressed later. These priorities will be subjective and will be for you and your service to agree upon.
5. In Column C, record the Impact that the task/action will have on compliance. Select high, medium or low from the drop-down list. To progress an action plan in a timely manner, services may choose to address tasks likely to have the greatest impact first, although this information must also be considered in conjunction with the Priority (Column B).
6. In Column D, the level of compliance for each task should be recorded in the drop-down list:
  a. If the task requires new work and no progress has yet been made, then the task should be recorded as ‘Non-Compliant’;
  b. If some work has been completed but the task is incomplete, then the task should be recorded as ‘Partially Compliant’; and
  c. If all work is complete, the task should be recorded as ‘Fully Compliant’.
7. The cell in D2 will automatically update to reflect the lowest level of compliance that exists in the task below. This information is then used to populate the 'Overall Compliance' graph at the top of the Dashboard.
8. Repeat the process for each Criteria tab.
Hidden Lists Tab
There is one hidden tab on the spreadsheet which can be revealed, if necessary, by 'Unhiding' (right click on the tabs). It contains the data used in drop-down lists and is also used to collate some data used for graphs.
The information on this sheet should not need to be altered, which is why the tab is hidden from view.
Worked example
The final tab on the sheet is a worked example put together by the subject matter experts involved in the development of the Fire Standard, it can be used as additional guidance for services when populating the implementation tool. This is only guidance to suggest what a service may consider in order to have processes in place to work toward achieving the Fire Standard. The onus remains with the service to formulate a robust strategy, decide complete relevant actions and put mechanisms in place to achieve the Fire Standard.

## Dashboard
| Please fill in the contact details below: | [6 empty] | Overall Compliance with Standard
Fire and Rescue Service
Contact Name
Contact Email Address
Contact Phone Number
Criteria | Description | Priority |  |  | Impact |  |  | Compliance
|  | Low | Medium | High | Low | Medium | High | Fully Compliant | Partically Compliant | Non Compliant | Chart
To achieve this Fire Standard a fire and rescue service must:
1a,b,c | Have a data governance framework or equivalent in place, and policies and procedures that includes, but is not limited to the following content: a) collection b) management c) storage and retrieval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1d,e,f | d) disposal e) security f) protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1g,h,I,j | g) publishing h) ethics i) sharing j) quality and assurance audit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Understand its data-related organisational risks and put in place controls to manage them | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Designate a senior leader who is responsible and accountable for developing and enacting the strategic approach to data management, within the service; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Have a nominated data owner(s), accountable for the quality, integrity, and protection of data and who are responsible for maintaining an accurate and complete information asset register; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Collaborate and partner with others, as and when appropriate; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Create a level of data literacy across the organisation, enabling employees to access and use data proportionate to their role; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7a, b, c | Have tools and systems in place that enable it to collect, interpret and analyse data, converting that data into meaningful business intelligence, to allow it to: a) make data available and in an accessible format to those who need it, both internally and externally; b) inform the development and maintenance of its community risk management plan; c) remain compliant with legislation and recognised data standards for the public sector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7d, e, f | d) provide national reporting and data submissions in line with government requirements and national data definitions, as and when they become available; e) operate and use its resources effectively; f) identify improvements to existing practices or to inform new ways of working; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7g, h, i | g) have effective business continuity and disaster recovery arrangements and processes; h) extract learning and identify trends or significant findings that might impact service delivery or the public directly and feed them into local, regional and national organisational learning arrangements and systems; and i) escalate issues locally, regionally or nationally, as and when required. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8a, b, c | Recruit, train, develop and maintain a competent and technical data capability to enable it to interpret, analyse and exploit data, in line with its governance framework by: a) ensuring those that provide the data capability have relevant skills, knowledge and experience in line with NFCC and other data related competency frameworks; b) embedding the appropriate ethical codes of practice and conduct into local policies, procedures, tailored guidance, and training materials; and c) record and monitor the competence of those who work with data and who are directly employed by the service, and support their continued professional development. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A fire and rescue service should:
9 | Present data and intelligence in a way that is meaningful for the intended audience; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Establish data sharing arrangements or agreements where beneficial to the community, to the service and others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Unlock improved and accessible ways of working and embrace innovation by: a) maximising opportunities gained from supporting the National Fire Chiefs Council (NFCC) network by sharing learning and experiences; b) identifying and accessing data outside of the service, which may enhance and contribute to continual improvement of service delivery; and c) staying informed of innovations in data technologies and trends. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A fire and rescue service may:
12 | Explore opportunities to enhance its technical data capability by utilising advanced analytical techniques. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DATA MANAGEMENT FIRE STANDARD
IMPLEMENTATION TOOL

## Lists (hidden)
Priority | Impact | Compliance
High | High | Fully Compliant
Medium | Medium | Partially Compliant
Low | Low | Non Compliant
|  |  | Criteria 1 | Criteria 2 | Criteria 3 | Criteria 4 | Criteria 5 | Criteria 6 | Criteria 7 | Criteria 8 | Criteria 9 | Criteria 10 | Criteria 11 | Criteria 12 | Criteria 13 | Criteria 14 | Criteria 15 | Criteria 16
|  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Fully Compliant | 16
|  |  | Partial Compliant | 0
|  |  | Non compliant | 0

## Criteria 1a,b,c
Have a data governance framework or equivalent in place, and policies and procedures that includes, but is not limited to the following content: a) collection b) management c) storage and retrieval | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 1/1
Task 1/2
Task 1/3
Task 1/4
Task 1/5
Task 1/6
Task 1/7
Task 1/8
Task 1/9
Task 1/10
Task 1/11

## Criteria 1d,e,f
d) disposal e) security f) protection | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 1/1
Task 1/2
Task 1/3
Task 1/4
Task 1/5
Task 1/6
Task 1/7
Task 1/8
Task 1/9
Task 1/10

## Criteria 1g,h,i,j
g) publishing h) ethics i) sharing j) quality and assurance audit | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 1/1
Task 1/2
Task 1/3
Task 1/4
Task 1/5
Task 1/6
Task 1/7
Task 1/8
Task 1/9
Task 1/10

## Criteria 2
Understand its data-related organisational risks and put in place controls to manage them | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 2/1
Task 2/2
Task 2/3
Task 2/4
Task 2/5
Task 2/6
Task 2/7
Task 2/8
Task 2/9
Task 2/10

## Criteria 3
Designate a senior leader who is responsible and accountable for developing and enacting the strategic approach to data management, within the service | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 3/1
Task 3/2
Task 3/3
Task 3/4
Task 3/5
Task 3/6
Task 3/7
Task 3/8
Task 3/9
Task 3/10

## Criteria 4
Have a nominated data owner(s), accountable for the quality, integrity, and protection of data and who are responsible for maintaining an accurate and complete information asset register; | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 4/1
Task 4/2
Task 4/3
Task 4/4
Task 4/5
Task 4/6
Task 4/7
Task 4/8
Task 4/9
Task 4/10

## Criteria 5
Collaborate and partner with others, as and when appropriate; | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 5/1
Task 5/2
Task 5/3
Task 5/4
Task 5/5
Task 5/6
Task 5/7
Task 5/8
Task 5/9
Task 5/10

## Criteria 6
Create a level of data literacy across the organisation, enabling employees to access and use data proportionate to their role; | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 6/1
Task 6/2
Task 6/3
Task 6/4
Task 6/5
Task 6/6
Task 6/7
Task 6/8
Task 6/9
Task 6/10

## Criteria 7a,b,c
Column1 | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 7/1
Task 7/2
Task 7/3
Task 7/4
Task 7/5
Task 7/6
Task 7/7
Task 7/8
Task 7/9
Task 7/10
Have tools and systems in place that enable it to collect, interpret and analyse data, converting that data into meaningful business intelligence, to allow it to:
a) make data available and in an accessible format to those who need it, both internally and externally;
b) inform the development and maintenance of its community risk management plan;
c) remain compliant with legislation and recognised data standards for the public sector

## Criteria 7d,e,f
Column1 | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 7/1
Task 7/2
Task 7/3
Task 7/4
Task 7/5
Task 7/6
Task 7/7
Task 7/8
Task 7/9
Task 7/10
d) provide national reporting and data submissions in line with government requirements and national data definitions, as and when they become available;
e) operate and use its resources effectively;
f) identify improvements to existing practices or to inform new ways of working

## Criteria 7g,h,i
Column1 | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 7/1
Task 7/2
Task 7/3
Task 7/4
Task 7/5
Task 7/6
Task 7/7
Task 7/8
Task 7/9
Task 7/10
g) have effective business continuity and disaster recovery arrangements and processes;
h) extract learning and identify trends or significant findings that might impact service delivery or the public directly and feed them into local, regional and national organisational learning arrangements and systems; and
i) escalate issues locally, regionally or nationally, as and when required.

## Criteria 8a,b,c
Column1 | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 8/1
Task 8/2
Task 8/3
Task 8/4
Task 8/5
Task 8/6
Task 8/7
Task 8/8
Task 8/9
Task 8/10
Recruit, train, develop and maintain a competent and technical data capability to enable it to interpret, analyse and exploit data, in line with its governance framework by:
a) ensuring those that provide the data capability have relevant skills, knowledge and experience in line with NFCC and other data related competency frameworks;
b) embedding the appropriate ethical codes of practice and conduct into local policies, procedures, tailored guidance, and training materials; and
c) record and monitor the competence of those who work with data and who are directly employed by the service, and support their continued professional development.

## Criteria 9
Present data and intelligence in a way that is meaningful for the intended audience; | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 9/1
Task 9/2
Task 9/3
Task 9/4
Task 9/5
Task 9/6
Task 9/7
Task 9/8
Task 9/9
Task 9/10

## Criteria 10
Establish data sharing arrangements or agreements where beneficial to the community, to the service and others | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 10/1
Task 10/2
Task 10/3
Task 10/4
Task 10/5
Task 10/6
Task 10/7
Task 10/8
Task 10/9
Task 10/10

## Criteria 11a,b,c
Column1 | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 11/1
Task 11/2
Task 11/3
Task 11/4
Task 11/5
Task 11/6
Task 11/7
Task 11/8
Task 11/9
Task 11/10
Unlock improved and accessible ways of working and embrace innovation by:
a) maximising opportunities gained from supporting the National Fire Chiefs Council (NFCC) network by sharing learning and experiences;
b) identifying and accessing data outside of the service, which may enhance and contribute to continual improvement of service delivery; and
c) staying informed of innovations in data technologies and trends.

## Criteria 12
Explore opportunities to enhance its technical data capability by utilising advanced analytical techniques. | Priority | Impact | Compliance | Work assigned to | Projected date for completion | Description of work needing to be done | Evidence of Compliance
Is FRS fully compliant with this Criteria? |  |  | Fully Compliant
Task 12/1
Task 12/2
Task 12/3
Task 12/4
Task 12/5
Task 12/6
Task 12/7
Task 12/8
Task 12/9
Task 12/10